## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No team members dropped. All members remained committed throughout the project. | open
| add new team members | New members may join late and need time to catch up | 2 | 3 | 2 | 24 | Team leader and all members | 2024-10-01 | Provide onboarding documentation and assign mentor for new members | No new members joined. Team remained stable. | open
| Lack of motivation or responsibility | Some members may not contribute equally | 3 | 4 | 3 | 18 | Team Leader | 2024-11-20 | Regular check-ins and clear task assignments | All members contributed actively. Work distribution was balanced. | open
Communication | duplicate work | Two members may accidentally do the same task | 3 | 3 | 2 | 18 | Team Leader, Configuration Leader | 2024-11-20 | Use task management system and regular sync meetings | Avoided through weekly meetings and clear task assignments | open
| worked on wrong components | Members may implement incorrect parts of the project | 2 | 4 | 3 | 24 | team leader and all members | 2024-11-20 | Clear documentation and code review process | Code review process prevented major issues. Minor adjustments made during implementation. | open
| useless work | Some work may not contribute to final deliverables | 2 | 3 | 2 | 24 | Team Leader, Configuration Leader | 2024-11-20 | Align all tasks with project requirements | All work contributed to deliverables. Code refactoring improved overall quality. | open
| inconsistent work | Different members may produce inconsistent outputs | 3 | 3 | 3 | 27 | Team Leader, Configuration Leader | 2024-11-20 | Establish coding standards and review guidelines | Code consistency improved through refactoring and standardization. AI usage annotations ensure transparency. | open
Requirements | unclear requirements | Requirements from professor may not be clear | 2 | 4 | 3 | 24 | Requirement Leader | 2024-10-15 | Regular clarification meetings with professor | Requirements clarified through multiple iterations. No major blockers. | open
| scope creep | Extra features may expand the project scope | 3 | 4 | 4 | 24 | Requirement Leader | 2024-11-20 | Strict scope management and feature prioritization | Scope remained controlled. AI chat feature added as planned enhancement. | open
| constant requirements changes | Frequent requirement changes may delay progress | 3 | 4 | 3 | 18 | Requirement Leader | 2024-11-20 | Flexible development approach and buffer time | Minor adjustments made. Risk management documentation updated to reflect changes. | open
Management | improper task assignments | Tasks may be assigned unfairly or incorrectly | 3 | 3 | 2 | 18 | Team Leader | 2024-11-20 | Balance workload based on member expertise | Tasks assigned based on strengths. Frontend/backend work distributed effectively. | open
| improper planning | Project planning may be unrealistic | 3 | 4 | 3 | 18 | Team Leader | 2024-11-20 | Review and adjust timeline regularly | Planning adjusted based on progress. Code refactoring added additional time but improved quality. | open
| lack of management skills | Leaders may lack sufficient management skills | 3 | 3 | 3 | 27 | Team Leader | 2024-11-20 | Learn management best practices and seek feedback | Management skills improved throughout project. Team coordination effective. | open
Technology competence | Not familiar with the framework used | Team unfamiliar with the chosen framework | 3 | 3 | 2 | 18 | Design and Implementation Leader | 2024-10-30 | Provide learning resources and code examples | Team became proficient with Vue.js and Spring Boot. Frontend code successfully refactored. | open
| Not familiar with the programming language used | Team unfamiliar with the programming language | 2 | 3 | 2 | 24 | Design and Implementation Leader | 2024-10-30 | Study language features and best practices | JavaScript/Java proficiency achieved. Code quality improved significantly. | open
| Not familiar with unit testing | Team unfamiliar with unit testing practices | 3 | 3 | 2 | 18 | Design and Implementation Leader | 2024-11-15 | Learn testing frameworks and write test cases | Testing implemented for critical components. Integration tests conducted. | open
| Other technology incompetence | General lack of technology knowledge | 3 | 4 | 3 | 18 | Team leader and all members | 2024-11-20 | Continuous learning and knowledge sharing | Technology skills improved. WebSocket, API integration, and authentication implemented successfully. | open
| Not familiar with Git | Team members may not be familiar with Git | 3 | 4 | 4 | 24 | Configuration Leader | 2024-09-30 | Git training and establish branching strategy | Team proficient with Git. Version control managed effectively throughout project. | open
Design and implementation | Improper design | System design may be incomplete or improper | 3 | 3 | 3 | 27 | Design and Implementation Leader | 2024-11-20 | Regular design reviews and refactoring | Design improved through refactoring. Frontend architecture modernized with better patterns. | open
| improper technology stack | Technology stack may not suit project needs | 3 | 4 | 3 | 18 | Design and Implementation Leader | 2024-10-15 | Evaluate technology choices and adjust if needed | Technology stack (Vue.js, Element Plus, Spring Boot) worked well. No major changes needed. | open
| Messy code | Code quality may be poor or inconsistent | 3 | 5 | 4 | 12 | Design and Implementation Leader | 2024-11-20 | Code refactoring and establish coding standards | Major code cleanup completed. 22 frontend files refactored with improved structure. AI usage documented in all files. | open
Testing | Not enough testing | Insufficient testing coverage | 2 | 2 | 2 | 32 | QA Leader | 2024-11-20 | Develop test plan and conduct thorough testing | Testing conducted for refactored components. Integration testing completed successfully. | open
Integration and deployment | Not enough time for integration and deployment | Insufficient time for final integration | 2 | 2 | 2 | 32 | Configuration Leader | 2024-11-20 | Allocate buffer time for integration | Integration completed on schedule. Development and production environments configured properly. | open
AI Usage Documentation | Incomplete AI usage tracking | AI tool usage may not be properly documented | 2 | 3 | 2 | 24 | All members | 2024-11-20 | Annotate all code files with AI usage ratios and maintain usage log | Completed comprehensive AI usage annotation across 22 frontend files. Created classification criteria based on code complexity. Usage log maintained. | open
Code Refactoring | Refactoring introduces new bugs | Code rewrite may introduce regressions | 3 | 4 | 3 | 18 | Design and Implementation Leader | 2024-11-15 | Thorough testing after refactoring and code review | Refactoring completed with minimal issues. Testing caught and resolved minor bugs. Code quality significantly improved. | open
Final Delivery | Time pressure for final deliverables | Insufficient time to complete all tasks | 2 | 4 | 3 | 24 | Team Leader | 2024-11-30 | Prioritize critical features and prepare documentation | On track for final delivery. Documentation and presentation materials in progress. | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.