## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/04/2025 - 9/24/2025 | Project Topic confirmed, technology stack selected. team member roles assigned | Microphone issues during the Zoom meeting | needs to find a suitable time to hold a group meeting during its initial formation. The team's initial work progress cannot be unified. | Schedule weekly group meetings 1-2 times per week to report progress, held either before or after Thursday's class for a quick group discussion. | 0 | 0 | 0 | 0 | 0 | 73 | 5 | 3 | 19 | 21 | 5 | 2 | 1 | 9 | 8
1 | 9/25/2025 - 10/16/2025 | The front-end and back-end have implemented user management functionality, including but not limited to user login, logout, and registration. | Incorrect use of GitHub has resulted in structural disarray. |  | Each individual creates their own branch on GitHub to develop features rather than working directly on the main branch. All code must undergo peer review before being merged. | [5 empty] | 157 | 131 | 26 | 14 | 13 | 21 | 54 | 16.5 | 26.5 | 12
2 | 10/05 - 11/06 | The demo is progressing well; the front-end has undergone significant modifications, including a complete refactoring, while the back-end has received minor revisions. | Some erroneous git pushes, redundant git branches, AI hallucination problem | Minor meeting member absent issue | A lot on front end re-fract | 5 | 5 | 1 | 1 | 1 | 130 | 20 | 2.5 | 15 | 14 | 24 | 22 | 30 | 14 | 10
3

## MIchael Yeh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/7 - 9/13 | 5 | 3 | 2 | 0 - Learned Vue.js basics and Element-UI overview 1 - Reviewed system frontend requirements 3 - Set up Google drive for co work 5 - Joined kickoff meeting, discussed team roles 6 - Set up Node.js, npm, Vue CLI | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | Used ChatGPT to understand Vue.js structure; Claude for comparing Vue vs React; results helped plan learning schedule | Reviewed SPPP; set up local dev env; researched Vue.js ecosystem; created learning roadmap | Unfamiliar with Vue.js; need domain UI knowledge; backend API unclear | Practice small Vue projects; study healthcare UI patterns; schedule API meeting | Finish Vue.js tutorial; learn Element-UI; design login/register mockups | 5
2 | 9/14 - 9/20 | 7 | 5 | 2 | 0 - Learned Vue Router, Vuex, Axios 1 - Discussed API endpoints and data models 2 - Designed login/register wireframes 5 - Presented design to team 6 - Initialized Vue project, ESLint/Prettier config | 2 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | Claude for healthcare UI design; ChatGPT for color palette and component structure; AI suggestions adjusted manually | Built UI mockups; set up Vue project; created component structure; selected healthcare theme | Schedule conflict; inconsistent design ideas; color scheme undecided; backend API not finalized | Use async chat; finalize design guideline; vote for color scheme; use mock data for now | Implement login page; set Axios config; create router; reusable forms | 6
3 | 9/21 - 9/27 | 4 | 1 | 3 | 0 - Element-UI form validation, SCSS practice 2 - Refined login design based on feedback 3 - Implemented login/register pages and layout 4 - Browser compatibility check 5 - Coordinated backend API design 6 - Set proxy and SCSS variables | 1 | 0 | 1 | 4 | 1 | 1 | 1 | 0 | Claude for form validation logic; ChatGPT for troubleshooting Element-UI and SCSS structure; helped generate store boilerplate | Built login/register UI; configured routing, Axios, Vuex; added healthcare background | Element-UI docs language barrier; CORS errors; validation bugs; non-responsive image | Used translated docs; fixed proxy; corrected form rules; applied responsive CSS | Add validation, loading state, password toggle, integrate API, handle notifications | 5
4 | 9/28 - 10/4 | 6 | 4 | 2 | 0- Practiced advanced Vue and Element-UI features (message box, dialog, form validation) 1- Discussed dashboard layout and user journey flow with team 2- Sketched dashboard wireframe and component layout 3- Coded homepage/dashboard skeleton using Element-UI layout + router view integration 4- Unit tested form validation and login flow with mock API responses 5- Weekly meeting to sync frontend progress and API integration timeline 6-Configured .env variables and Axios baseURL for staging | 1 | 1 | 1 | 2 | 0.5 | 0.5 | 1 | 0 | Used ChatGPT for Element-UI layout examples and router guards; Claude for mock data JSON schema generation; tools helped save setup time and reduce errors | Completed login/register integration with mock API; built initial dashboard layout and navbar structure | Routing refresh caused 404; form validation not triggering on blur | Fixed router mode to history; updated validation triggers and watchers | Add dashboard widgets (vitals chart, notifications); implement user profile page; connect to real backend API | 7
5 | 10/5 - 10/12 | 7 | 5 | 2 | 0- Studied Axios interceptors, JWT token handling, and async/await patterns in Vue 1 - Reviewed backend API documentation and confirmed response formats with backend team 2 - Adjusted dashboard layout for API-driven data display (vital signs & alerts) 3 - Implemented API integration for login and dashboard; added Axios interceptors for authentication; displayed user data dynamically on dashboard 4 - Tested login token persistence and API error handling; verified real backend connection 5 - Coordinated with backend to debug API response mismatch and update endpoint parameters 6 - Set up .env.development and .env.production configs for API base URLs | 1 | 1 | 1 | 2 | 1 | 0.5 | 0.5 | 1 | Used ChatGPT to debug Axios interceptor token injection; Copilot to autocomplete API request logic; both improved development efficiency and reduced syntax errors | Finished login authentication with backend API; implemented dashboard data binding with real API responses; added loading and error states | Token expired issue after page refresh; inconsistent API response keys from backend | Added token refresh logic; notified backend team to align response field names | Add user profile editing page; connect profile update API; improve responsive layout for mobile view | 7
6 | (10/13 - 10/19) | 8 | 6 | 2 | 0 - Studied Vue composables, mobile-first responsive design patterns, and Element-UI form components 1 - Analyzed user profile requirements and data validation rules with backend team 2 - Designed user profile page layout with form sections (personal info, medical history, settings) 3 - Implemented user profile page with editable forms; integrated profile update API; added image upload for avatar; implemented mobile responsive layout with media queries 4 - Tested profile update workflow across devices; validated form inputs and API error handling 5 - Discussed UI/UX improvements and accessibility features in team meeting 6 - Configured image upload storage settings and file size limits | 1 | 1 | 1 | 3 | 1 | 0.5 | 0.5 | 0 | Used Claude for responsive CSS grid layout suggestions; ChatGPT for image upload validation logic and compression; Copilot for form binding boilerplate; tools significantly improved mobile layout quality | Completed user profile page with full CRUD functionality; implemented responsive design for mobile/tablet views; added avatar upload feature; enhanced form validation | Image upload size exceeded backend limit; responsive layout broke on iPad view; profile data not refreshing after update | Added client-side image compression; fixed flexbox issues with specific breakpoints; implemented manual data refresh after successful update | Implement vital signs chart using Chart.js or ECharts; add notifications/alerts panel; create appointment scheduling interface; improve loading states | 8
7 | (10/20 - 10/26) | 9 | 7 | 2 | 0 - Learned WebSocket integration in Vue, real-time data handling patterns, and Element-UI notification components 1 - Reviewed AI Assistant chat requirements and WebSocket API specifications with backend team; analyzed health records data structure 2 - Designed AI Assistant chat interface with message history display; sketched health records management page layout with data visualization 3 - Implemented AI Assistant chat interface with WebSocket connection; built health records management page with CRUD operations; added real-time message display with auto-scroll; integrated health data API endpoints; implemented data visualization for vital signs trends 4 - Tested WebSocket connection stability and reconnection logic; validated health records form validation and API integration; verified real-time chat functionality across browsers 5 - Coordinated with backend on WebSocket event handling and message format; presented AI chat demo to team 6 - Configured WebSocket connection URL for different environments; set up error handling and reconnection strategy with exponential backoff | 1.5 | 1 | 1 | 3.5 | 1 | 0.5 | 0.5 | 0 | Used ChatGPT for WebSocket implementation examples and reconnection logic; Claude for health data visualization component suggestions; Copilot for message handling boilerplate code; AI tools helped reduce debugging time and improve real-time communication reliability | Completed AI Assistant chat interface with WebSocket real-time communication; implemented health records management page with full CRUD functionality; added vital signs trend visualization; enhanced chat UI with message typing indicators and timestamps; built connection status monitoring | WebSocket connection dropped on network change; chat history not persisting after refresh; health records form validation inconsistent; data visualization performance lag with large datasets; connection timeout not properly handled | Implemented WebSocket reconnection with exponential backoff strategy; added localStorage for chat history caching; unified form validation rules using Element-UI validators; optimized chart rendering with data pagination; added connection timeout detection and user notification | Implement role-based access control on frontend; build user management interface for admin role; add permission checking for routes and components; create doctor dashboard with patient data access; enhance security with JWT token refresh | 8
8 | (10/27 - 11/2) | 8 | 6 | 2 | 0 - Studied Vue route guards, permission-based rendering patterns, and JWT token refresh mechanisms 1 - Analyzed role-based access control requirements from Software Design Document; discussed permission matrix with requirement manager and backend team 2 - Designed admin user management interface with role assignment; created doctor dashboard wireframe with patient list and health data access; planned permission-based component visibility logic 3 - Implemented route-level permission guards using Vue Router navigation guards; built admin user management page with user list, role assignment, and user editing; created doctor dashboard with patient search and health records access; added JWT token auto-refresh interceptor; implemented permission-based UI rendering (v-if directives for role-specific features) 4 - Tested permission enforcement across different user roles (admin, doctor, user); validated unauthorized access blocking; verified token refresh workflow; conducted cross-role navigation testing 5 - Demo'd role-based features to team; gathered feedback on UX for permission-denied scenarios 6 - Configured route meta fields for permission requirements; set up Vuex store for user role and permissions caching | 1 | 1 | 1 | 3 | 1 | 0.5 | 0.5 | 0 | Used Claude for route guard logic and permission checking patterns; ChatGPT for JWT token refresh implementation and interceptor setup; Copilot for admin UI table operations boilerplate; tools significantly improved security implementation accuracy and reduced authentication bugs | Completed role-based access control system with route guards; built admin user management interface with full CRUD for users and roles; created doctor dashboard with patient health data access; implemented JWT token auto-refresh mechanism; added permission-based UI component rendering; enhanced unauthorized access handling with friendly error messages | Token refresh caused duplicate requests; permission check slowed down route navigation; admin table pagination not working with search filter; doctor role could access admin routes briefly before redirect; permission state not updating after role change without logout | dded request queue to prevent duplicate refresh calls; optimized permission check with Vuex caching and async lazy loading; fixed pagination reset on search; strengthened route guard with synchronous permission verification; implemented real-time permission sync with backend on critical actions | Integrate Google OAuth login flow; add password change functionality; implement profile update with photo upload; create forgot password workflow; enhance overall UI/UX with loading states and error boundaries; conduct comprehensive cross-browser testing | 7

## Zhiyao Song
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 7 | 6 | 1 | 0 - Learning Agile, Github 1 - Brainstorming project topic 1 - Discussed project requirements 2 - Technical stack for project | 3 | 3 | 1 | [5 empty] | Analyze the technical stack required for the project using ChatGPT. |  |  |  | 1. Finish Iteration 0 2. Prepare the presentation for Iteration 0 | 8
2 | 9/18 - 9/24 | 8 | 7 | 1 | 0 - Review course material 1 - Work on SPPP 1 - Work on Lab1 1 - Prepare the presentation 5 - Define clear requirements for the project 6- Set up Github | 2 | 4 |  |  |  | 1 | 1 | [5 empty] | Begin creating the demo | 12
3 | 9/25 - 10/1 | 19 | 18 | 1 | 0 - Learning/Review Spring Boot, MyBatis ORM and SQLite 1 - Analyze user authentication, role permissions, and database structure requirements 3 - Implement a data access layer consisting of 3 entity classes and 3 Mapper interfaces. 4 - Test database connection and Mapper interface functionality 5 - Weekly group meeting 6 - Configure the Spring Boot project environment and Maven dependencies | 2 | 2 |  | 8 | 4 | 1 | 2 |  | Utilize Cursor to assist in backend environment setup, and leverage ChatGPT for detailed optimization. | Complete database design, entity class development, and data access layer to establish the project's technical stack foundation. | Resolve three technical issues: SQLite connection pool configuration, MyBatis mapping paths, and database initialization. | All configuration issues have been resolved, laying a solid foundation for business logic development. | Continue backend development, focusing on core business logic and security. | 20
4 | 10/2 - 10/8 | 27 | 26 | 1 | 0 - Learning BCrypt Password Encryption and Google OAuth Integration Techniques 1 - Analyze certification processes, permission verification, and security mechanism requirements 2 - Design the service architecture, authorization verification process, and security mechanisms. 3 - Implement the business logic for AuthService and the API interfaces for three Controllers. 4 - Testing certification functions and permission verification mechanisms 5 - Weekly group meeting | 3 | 3 | 4 | 14 | 2 | 1 |  |  | Using ChatGPT to learn new technology stacks | Implement three core business modules—authentication services, user management, and role-based permissions—along with security mechanisms. | Solving four business challenges: Google OAuth integration, password encryption, role assignment, and data validation | Core functionality development is complete, and all business logic issues have been resolved. | Continue backend development and design | 25
5 | 10/9 - 10/15 | 17.5 | 17 | 0.5 | 0 - Learning RESTful API Best Practices and Security Testing Methods 1 - Analyze API interface specifications and performance optimization requirements 3 - Enhance the AuthController, strengthen security mechanisms, and refactor the code. 4 - Conduct API integration testing and performance testing | 2 | 2 |  | 10 | 3 | 0.5 |  |  |  | Enhance API exception handling, strengthen security mechanisms, improve code quality, and ensure documentation completeness. | Resolved three issues: exception handling, security risks, and API specifications. Test coverage is partially complete. | User management is largely complete, with only test coverage requiring subsequent improvement. | Continue backend development and design | 20
6 | 10/16 - 10/22 | 16 | 15 | 1 | 2 - Backend design 3 - Start to implementation of the body information management module 5 - Weekly group meeting | 0 | 0 | 5 | 10 | 0 | 1 |  |  | Employing ChatGPT to assist in analysing the prioritisation of module development | Collaborated with members of the backend development team to establish the subsequent module development plan and commenced work on the body information management module. | Resolved issues: 1. Priority of Module Design and Development | All configuration issues have been resolved | Continue backend development and design | 15
7 | 10/23 - 10/29 | 13 | 12 | 1 | 1 - Work on Lab3 2 - Continue backend design 3 - Continue implementation module 5 - Weekly group meeting | 0 | 1 | 3 | 8 | 0 | 1 |  |  | Employing ChatGPT and Cursor to assist in the design and development of backend modules. | Collaborate with team members to complete the design and development of the backend modules. | Resolved issues: 1. Priority of Module Design and Development | All configuration issues have been resolved | Continue backend development and design | 15
8 | 10/30 - 11/6 | 15 | 13 | 2 | 0 - Learning the Vue front-end framework 3 - Collaborate with front-end developers to optimise front-end code 4 - Performing basic testing on the backend using Postman 5 - Weekly group meeting 5 - Discussions with the front-end team 6 - Resolving front-end and back-end environment configuration issues | 4 |  |  | 5 | 2 | 2 | 2 |  | Using ChatGPT, Cursor to learning Vue framework and resolving environmental configuration issues | Collaborate with front-end developers to optimise and enhance existing front-end code. Resolving front-end and back-end startup failures caused by environmental issues | Resolved issues: 1. The front-end code is not sufficiently concise and clear. 2. The front-end visual effects are not sufficiently aesthetically pleasing. 3. Front-end and back-end environment configuration issues | All issues have been resolved, and the project is now progressing steadily. The project can proceed as planned. | Researching database security issues | 20

## Mark Pimpa
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/11 - 9/17 | 6 | 5 | 1 | 0 - Familarizing Github 1 - Brainstorming project topic 1 - Discussed project requirements | 3 | 3 | [6 empty] | Using ChatGPT as a guide to understand several GitHub commands. |  |  |  | Complete Iteration 0 Prepare the presentation for Iteration 0 | 8
2 | 9/18 - 9/24 | 7 | 6 | 1 | 0 - Review course material 1 - Work on GitHub's team.md 1 - Work on Lab1 5 - Define clear requirements for the project | 2 | 4 |  |  |  | 1 | [6 empty] | Begin creating the demo | 3
3 | 9/25 - 10/1 | 4 | 3 | 1 | 2 - Start designing project 5 - Figuring out project user stories 5 - Weekly Meeting |  |  | 2 |  |  | 2 |  |  | Using ChatGPT to analyze the reference project we used as study case |  |  |  | Analyze the reference project and begin working on demo | 3
4 | 10/2 - 10/8 | 3 | 2 | 1 | 5 - Add missing document in iteration 0 5 - Weekly Meeting | [5 empty] | 3 | [6 empty] | Prepare for the presentation for iteration 1 | 3
5 | 10/9 - 10/15 | 3 | 2 | 1 | 5 - Summarize and prepare the presentation 5 - Weekly Meeting | [5 empty] | 3 |  |  | Using ChatGPT to help organize presentation script. |  |  |  | Complete Iteration 1 | 3
6 | 10/16 - 10/22 | 2 | 1 | 1 | 3 - Update the frontend API service 5 - Weekly Meeting |  |  |  | 1 |  | 1 |  |  | Update the frontend API service using ChatGPT assist
7 | 10/23 - 10/29 | 2 | 1 | 1 | 3 - Update the frontend API service 5 - Weekly Meeting |  |  |  | 1 |  | 1 |  |  | Update the frontend API service using ChatGPT assist
8 | 10/30 - 11/6 | 3 | 2 | 1 | 3 - Refactoring UI and Front-end 5 - Weekly Meeting 5 - Summarize and prepare the presentation |  |  |  | 2 |  | 1 |  |  | Preparing for presentation

## YChen
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/7 - 9/13 | 5 | 3 | 2 | 0 - learn Java Spring Boot, Docker 1 - explore overlap among teamates's capabilities 3 - Set up Google drive for co work 5 - make project plan, recruit members, set up dashboard, portal available hours, gather contact infomration from members; set up communication rules and workflow 6 - git repo set up | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | Mostly use AI to assist self learning and team brain strom. No AI coding involved | 1. Write Management Plan of SPPP. 2. Allocate tasks according to team roles. 3. Create Wechat group and join Discord group 4. Set up organizational repo. | 1. Me not familiar with Java backend gateway. 2. As a team leader, I realized that assigning specific tasks to the front-end and back-end was difficult because different team members were familiar with different processes. | Use chat-gpt to checklist items to reduce cognitive load of document reading. | Finalize the specific technology stack And do ppt | 5
2 | 9/14 - 9/20 | 5 | 3 | 2 | 3 - Do ppt 5 - Finalize the specific technology stack with team members and identify unfamiliar parts | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Use AI to generate some icons in PPT, etc. | 1. Review connection between high-level customer demand and proposed analysis process. 2. Downloaded the Spring Boot project sample code and distributed it to team members 3. Finish PPT 4. Do presentation with Song | 1. Temmates are vastly different in schdules, implementation skills, domain of expertise, language, and attitudes. Aligning these factors towards product delivery requires a unifying motivation. Especially the backend part 2. Realizing that AI features may be difficult to achieve due to privacy concerns, this will be reflected in the presentation. | 1.Urge team members to learn the missing technologies on their own. Instruct each team member to observe the sample code on the Internet and study it. 2. Still thinking about it. Time may tell | 3. Integrate different components of the project. 5. Address team conflicts, e.g., scheduling, response time especially for part time guy and non-CS undergrad . | 5
3 | 9/21 - 9/27 | 4 | 1 | 3 | 3 - Try deploy OCR and Azure on backend. Experimental 5 - backend exp code | 1 | 0 | 0 | 3 | 1 | 2 | 1 | 0 | Learn Claude Codea and Azure. I only use Trae and Windsurf before. Use geminito run code review agsint SPPP writting by Song | 1. PDF reading capabilities are now publicly available on the web. | AI/ AIIDE creates a lot of redundant files and tries a lot of wrong approaches. I really need to learn how to write "Rule" in Cursor. It work differently compared with TRAE IDE | Keep prompt template that points out project configurations, implementation steps, and testing to reduce the time and scope where AI randomly tries different solutions. | test and merge all the Pushes on github. | 5
4 | 9/28 - 10/4 | 5 | 2 | 4 | 4 - test branch. 5 - re-allocates temmates tasks when the original person in charge is too busy. 5 - teach how to use AI effectively. 6 - write reports 6 - communicate with front end guy | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Use AI to write test branches Help specifiy | 1. PDF reading capabilities are now publicly available on the web. | AI/ AIIDE creates a lot of redundant files and tries a lot of wrong approaches. I really need to learn how to write "Rule" in Cursor. It work differently compared with TRAE IDE | Keep prompt template that points out project configurations, implementation steps, and testing to reduce the time and scope where AI randomly tries different solutions. | test and merge all the Pushes on github.
5 | 10/5 - 10/11 | 6 | 4 | 2 | 2 - Database schema design for health data tables 3 - Backend user/role/permission implementation 6 - SQLite configuration and MyBatis setup | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | Used Cursor AI for database schema design and MyBatis configuration. Claude helped with SQL optimization. Very helpful for reducing syntax errors. | 1. Designed health data tables (j_body, sport_info, detail) 2. Configured SQLite with Hikari connection pool 3. Set up MyBatis XML mappers | Backend database connection issues with SQLite path configuration | Fixed SQLite path and tested connection successfully | Complete user/role/permission controllers Implement authentication service | 6
6 | 10/12 - 10/18 | 7 | 5 | 2 | 3 - AuthController and UserController development 3 - Google login integration 4 - Backend API testing with Postman | 0 | 0 | 1 | 4 | 2 | 1 | 0 | 0 | Used Trae AI for AuthController implementation. GitHub Copilot for Google OAuth integration. AI suggestions were accurate for Spring Security configuration. | 1. Implemented AuthController with login/register endpoints 2. Added Google OAuth2 integration 3. Created UserController with CRUD operations 4. Tested APIs with Postman | Google OAuth callback URL configuration issues | Resolved OAuth redirect URI and tested successfully | Develop RoleController and permission management Start frontend Vue.js setup | 6
7 | 10/19 - 10/26 | 12 | 9 | 3 | 0 - learning: Reviewed Vue 3 composition API and Vite project structure. 1 - requirement analysis: Clarified refactor goals and maintainability needs. 2 - design: Proposed SPA architecture, folder layout, routing schema. 3 - implementation: Scaffolded layouts/router/store; baseline components. 4 - test: Manual smoke tests for navigation and build output. 5 - communication/management: Team syncs; prepared refactor/challenges slides. 6 - configuration/environment: Vite config, ESLint/Prettier baseline. 7 - unclassified: none. | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 0 | Used Copilot and ChatGPT to audit legacy Vue code and compare refactor options; Trae assisted routing/layout scaffolding. Guidance accelerated component structure decisions. | Proposed Vue 3 SPA architecture; created baseline with layouts/router/store; drafted refactor plan; prepared Iteration-3 slides on refactor rationale and technical challenges. | Legacy code mixed options/composition APIs, duplicated API clients, CSS conflicts leading to fragile UI and low maintainability. | Agreed to full refactor with standardized folders; scheduled pair sessions; froze risky legacy features; migrate features incrementally while keeping trunk green. | Auth layout and navigation (3h); Dashboard shell scaffolding (2h); Typed API client (1h). | 6
8 | 10/26 - 11/2 | 16 | 13 | 3 | 0 - learning: Router guards patterns and Axios interceptors best practices. 1 - requirement analysis: Confirmed pages and authentication flows with team. 2 - design: Error boundary and token refresh flow design. 3 - implementation: Rewrote app shell; ported Login/Register/Dashboard; added interceptors. 4 - test: Guard/refresh behaviors; CORS validation in dev. 5 - communication/management: Updated refactor plan; reviewed PRs. 6 - configuration/environment: Vite proxy, env configs, shared CSS tokens. 7 - unclassified: none. | 1 | 0 | 3 | 9 | 2 | 1 | 0 | 0 | Copilot generated typed Axios service wrappers; ChatGPT helped with Vue Router guards and edge cases; Trae improved search and quick fixes during refactor. | Rewrote app shell, navigation and route guards; added error boundary; ported Login/Register/Dashboard pages; unified Axios interceptors and env-based config. | Guard recursion loops, token refresh race, dev CORS mismatch, style clashes across legacy components. | Fixed guard loops; implemented refresh queue; configured Vite proxy and dev CORS; introduced CSS scopes and shared design tokens. | Bind dashboard to backend (4h); Unit tests for services (2h); Finalize slides (1h).
9 | 11/02 - 11/08 | 15 | 12 | 3 | 0 - learning: OAuth edge cases and DTO alignment. 1 - requirement analysis: Mapped backend data to dashboard requirements. 2 - design: Typed API layer and store reset strategy. 3 - implementation: Connected services; health record listing; refined store/UI. 4 - test: Fixed 401 refresh issues; CI build checks; unit test stubs. 5 - communication/management: Prepared and delivered Iteration-3 presentation. 6 - configuration/environment: Build scripts and pipeline simplification. 7 - unclassified: none. | 1 | 0 | 2 | 8 | 3 | 1 | 0 | 0 | Used Copilot/ChatGPT for test stubs and error handling patterns; Trae searches helped detect dead components and wiring issues during debugging. | Connected dashboard to backend services; implemented health record listing; stabilized OAuth login; prepared and delivered Iteration-3 presentation on refactor and tech challenges. | Intermittent logout/401 after refresh; mismatched DTO fields; a few failing builds in CI. | Aligned request/response types; improved error handling and store reset on logout; fixed build scripts and simplified pipeline. | Stabilize auth/dashboard (3h); Charts and alerts (2h); Plan Iteration-4 deliverables (1h). | 8

## HanxiaoWang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/7 - 9/13 | 6 | 4 | 2 | 0 - learn project background and software development lifecycle 1 - understand team roles and project scope 6 - get familiar with GitHub and other project tools | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Used ChatGPT to review software engineering concepts and understand Git commands. | Set up GitHub access and explored project documentation. | Difficult to understand overall project structure at first. | Team members helped explain project goals and structure in group meeting. | Get familiar with Docker and UML tools. | 5
2 | 9/14 - 9/20 | 7 | 5 | 2 | 0 - explore project repo and structure 6 - configure environment for development 5 - communicate with teammates about tasks and presentation plan | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | Used ChatGPT to clarify Docker usage and UML diagram concepts. | Configured local development environment and learned how to run the project. | Still some technical issues during setup. | Resolved setup problems with help from teammates. | Start preparing for next presentation and divide responsibilities. | 5
3 | 9/21 – 9/27 | 8 | 5 | 3 | 0 - review frontend repo structure; 2 - review UI layout plan; 3 - set up initial React components for login/register; 5 - communicate with backend to align API data format | 0 | 0 | 1 | 3 | 0 | 1 | 1 | 0 | Used ChatGPT to check React form validation syntax and CSS layout examples. | Built initial login/register page layout and tested API placeholders. | Minor confusion about props and state handling in React. | Resolved with teammate discussion and online examples. | Complete form logic and API connection. | 6
4 | 9/28 – 10/4 | 9 | 6 | 3 | 2 - refine page design; 3 - implement login/register components; 4 - test API connectivity; 5 - attend weekly frontend meeting | 0 | 0 | 1 | 4 | 1 | 1 | 1 | 0 | Used ChatGPT to debug fetch() API request errors and cross-origin setup. | Completed working login/register flow connected to backend API. | CORS issue between frontend and backend. | Resolved by adjusting Spring Boot CORS config. | Start UI styling improvement and responsiveness check. | 7
5 | 10/5 – 10/11 | 10 | 7 | 3 | 3 - integrate backend testing results; 4 - debug input validation; 5 - collaborate on presentation material | 0 | 0 | 0 | 4 | 2 | 1 | 2 | 0 | Used ChatGPT to format Postman test results and summarize API behavior for slides. | Polished onboarding UI and verified registration/login success messages. | Frontend validation edge cases. | Fixed regex and added error messages. | Finalize Iteration 1 slides and demo flow. | 8
6 | 10/12 – 10/16 | 9 | 6 | 3 | 2 - refine slide visuals; 3 - prepare frontend demo flow; 5 - coordinate with team for presentation delivery | 0 | 0 | 1 | 3 | 0 | 2 | 1 | 0 | Used ChatGPT to refine presentation script and improve slide language. | Prepared final demo and delivered frontend portion in Iteration 1 presentation. | Time pressure before presentation. | Rehearsed as a team and finalized content. | Begin planning profile dashboard for Iteration 2. | 7
7 | 10/17 - 10/23 | 10 | 7 | 3 | 1 - review and update risk management documentation structure; 2 - analyze frontend code for rewrite planning; 3 - begin refactoring frontend utility files; 5 - coordinate with backend team on code cleaning scope | 0 | 2 | 1 | 3 | 0 | 0 | 1 | 0 | Used ChatGPT to review risk management best practices and template formats; Used Cursor AI to analyze frontend code structure | Updated risk documentation with new threats and mitigation strategies; Created frontend refactor plan | Backend coordination took longer than expected | Resolved through multiple team discussions and code reviews | Continue frontend code rewrite and backend cleaning coordination | 8
8 | 10/24 - 10/30 | 12 | 9 | 3 | 1 - finalize risk management document updates; 3 - rewrite frontend authentication module; 3 - assist backend team with code organization; 4 - test refactored authentication flow; 5 - weekly progress sync | 0 | 1 | 0 | 6 | 2 | 0 | 0 | 0 | Used Cursor AI to rewrite auth.js and request.js with improved error handling; Used ChatGPT to document code changes | Completed risk management document update; Rewrote authentication utilities with better structure | Some authentication edge cases needed additional handling | Fixed by adding comprehensive validation logic | Start rewriting view components and plan AI annotations | 9
9 | 10/31 - 11/20 | 14 | 11 | 3 | 3 - rewrite all frontend view components and API modules; 3 - help clean up backend controller code; 3 - annotate AI usage ratios in all 22 frontend files; 4 - comprehensive testing for rewritten components; 1 - review overall project documentation; 5 - team meetings on project status | 0 | 1 | 0 | 8 | 2 | 0 | 0 | 0 | Used Cursor AI extensively to rewrite 22 frontend files and add detailed AI generation ratio comments; Used ChatGPT to create AI annotation guidelines and ensure consistent formatting | Completed frontend code rewrite (Login, Register, Profile, Dashboard, AiChat, BodyInfo, BodyNotes, SportInfo, UserManagement, MainLayout, all API files); Annotated all 22 files with clear AI/manual ratio documentation; Cleaned 3 backend controllers | Balancing code rewrite quality with AI annotation consistency was challenging | Created classification guidelines based on code complexity; Systematically reviewed each file for accurate ratio assignment | Prepare for final project delivery and presentation | 8

## Haopeng Zeng
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/7 - 9/13 | 6 | 4 | 2 | 0 - learn software develop life circle 1 - explore overlap among teamates's capabilities 6 - Set up Github 5 - Brainstorm project ideas | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Mostly about brain strom. No AI coding involved | Set up Github repo figure out project topic | its difficult to split each part to each teamate especially we have different tech stacks | we all agree to do the project base on Java SpringBoot | Finalize the specific technology stack And do ppt | 5
2 | 9/14 - 9/20 | 6 | 4 | 2 | 6 - setup repo structure 6 - setup backend overall structure 5- decide all tech stacks with whole team | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | Use AI to generate some ideas | 1. Review every section in the SPPP and provide feedback 2. Review presentation for iteration 0 3. Review SpringBoot structure with whole team | time schedule with each teamate | we have all agree to meet after class and at least an online meeting each week | desing the sql interaction done by the backend go through all the backend requirement for the project | 5
3 | 9/21 - 9/27 | 7 | 4 | 3 | 5 - started project design 5 - go over the project structure with whole team | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | Use AI to learn some backend structure and code | split each part of the project | its still difficult to decide each member's part | Having more meeting to figure out | figure out individual work | 5
4 | 10/02 - 10/09 | 7 | 4 | 3 | 2 - continue with the project design 2 - set up the requirement strucuture on Github for the team 5 - weekly meeting with whole team |  |  | 3 |  |  | 1 |  |  | Use AI to generate some ideas for develop project requirement | figure out project structure for lab2 for the whole team working on project backend | what shoule be inside iteration1 | Having more meeting to figure out | finish iteration1 | 5
5 | 10/12 - 10/17 | 7 | 4 | 3 | 2 - continue with the project backenddesign 2 - set up the Docker enviroment invovled in the project 5 - weekly meeting with whole team |  | 2 | 2 |  |  | 3 |  |  | Use AI to help set up docker files and setting | upload docker files that involved our tech stacks designing databse structure | handling all the enviroment problem inside docker is quite challenging | getting lots of help from AI tools and set up the docker files successfully | finish database design and try to connect front end and back end function | 5
6 | 10/18 - 10/24 | 7 | 4 | 3 | 2 - continue with the project backend design 2 - set up the unit test for lab 3 5 - focusing what should be presented in Iteration 2 5 - weekly meeting with whole team |  | 2 | 2 |  |  | 3 |  |  | Use chatGPT to help setting up unit test | update latest docker file | frontend code and structure is too complicated and hard to understand | reorganized the all frontend structure | preperaing what we going to present in iteration2 | 7
7 | 10/25 - 10/31 | 7 | 4 | 3 | 2 - continue with the project backend design 2 - finish lab 3 5 - focusing what should be presented in Iteration 2 5 - weekly meeting with whole team 6 - update the docker composer file |  | 2 | 2 |  |  | 3 |  |  | Use chatGPT to help coding | finish lab3 unit test, figure out what we should present in interation 2 | communication wise | planning to have more stand-up meeting | finish the presentation ppt and also the DEMO | 8
8 | 11/1 - 11/6 | 8 | 5 | 3 | 2 - finish DEMO 2 - update DB design 2 - reorganize the Github repo 5 - presentation ppt for iteration2 4 - testing for login function |  |  | 5 |  | 1 | 2 |  |  | Use ChatGPT for coding | presentation for iteration2 and DEMO |  |  | Make sure what we need to do in next iteration | 5

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments